## BFCM Checklist
Shopify BFCM 2026 Planning Checklist
By Webiots — companion to "Shopify BFCM 2026: The Complete Guide + 25-Step Checklist". Black Friday: Fri Nov 27, 2026 · Cyber Monday: Mon Nov 30, 2026.
How to use: edit Owner, Deadline, Status, Test result and Notes (yellow columns). Deadlines are a suggested schedule; adjust them to your store. Pick Status and Priority from the dropdowns.
Progress: | 1 of 46 tasks done |  | 2.174%
Task | Category | Deadline | Owner | Priority | Status | Test result | Notes
Review last year's BFCM revenue, AOV, conversion and best sellers | Strategy | 2026-10-25 | Marketing | High | Done | Pass | Example row: 2025 AOV was $72; best seller sold out on Saturday.
Set revenue, AOV, conversion and new-customer goals | Strategy | 2026-10-25 | Marketing | High | Not started
Set a margin floor (lowest acceptable margin after discounts, fees and ads) | Strategy | 2026-10-25 | Finance | High | Not started
Run best seller through the discount vs bundle vs add-on profit calculator | Strategy | 2026-10-28 | Finance | High | Not started
Choose hero products to feature in ads, emails and landing pages | Strategy | 2026-10-28 | Marketing | High | Not started
Forecast demand by SKU and reorder stock | Operations | 2026-10-31 | Ops | High | Not started
Order packaging, mailers, labels and gift-with-purchase stock | Operations | 2026-10-31 | Ops | Medium | Not started
Pick one clear main offer and write its terms (min spend, exclusions, end date) | Offers | 2026-10-31 | Marketing | High | Not started
Create BFCM discounts in Shopify (Discounts) with start and end times | Offers | 2026-11-10 | Marketing | High | Not started
Set which discounts can combine (product, order, shipping) | Offers | 2026-11-10 | Marketing | High | Not started
Set up bundles, volume tiers and paid add-ons on top products | Offers | 2026-11-10 | Store/Dev | Medium | Not started
Set free shipping threshold just above current AOV (Settings > Shipping and delivery) | Offers | 2026-11-10 | Ops | Medium | Not started
Build BFCM landing page or sale collection (keep it hidden until launch) | Store | 2026-11-10 | Store/Dev | High | Not started
Update announcement bar and homepage hero for launch day | Store | 2026-11-10 | Store/Dev | Medium | Not started
Publish gift guides by recipient and price | Store | 2026-11-10 | Marketing | Medium | Not started
Optimize product pages: deal near price, delivery estimate, return policy | Store | 2026-11-10 | Store/Dev | Medium | Not started
Write emails and SMS for teaser, VIP, launch, reminders, Cyber Monday, last chance | Marketing | 2026-11-10 | Marketing | High | Not started
Prepare ad creatives (several versions) and retargeting audiences | Marketing | 2026-11-10 | Marketing | High | Not started
Brief creators with dates, codes and tracking links | Marketing | 2026-11-10 | Marketing | Low | Not started
Launch early-access sign-up pop-up or page | Marketing | 2026-11-01 | Marketing | Medium | Not started
Test: automatic discount applies on product page, cart and checkout | Testing | 2026-11-18 | Store/Dev | High | Not started
Test: discount codes work and invalid codes show a clear message | Testing | 2026-11-18 | Store/Dev | High | Not started
Test: discount combinations stack only as planned | Testing | 2026-11-18 | Store/Dev | High | Not started
Test: add-on prices appear correctly in cart, checkout and order | Testing | 2026-11-18 | Store/Dev | High | Not started
Test: free shipping threshold triggers at the right cart total | Testing | 2026-11-18 | Store/Dev | High | Not started
Test: full order on a phone (product page to confirmation email) | Testing | 2026-11-18 | Store/Dev | High | Not started
Test: purchase tracked in Shopify Analytics, GA4 and ad pixels with UTMs | Testing | 2026-11-18 | Marketing | High | Not started
Check key pages in Google PageSpeed Insights and compress heavy images | Testing | 2026-11-18 | Store/Dev | Medium | Not started
Remove unused apps; duplicate live theme as a backup | Store | 2026-11-18 | Store/Dev | Medium | Not started
Freeze theme and app changes | Store | 2026-11-18 | Store/Dev | High | Not started
Turn on abandoned checkout emails (Marketing > Automations) | Marketing | 2026-11-18 | Marketing | High | Not started
Confirm carrier holiday deadlines and publish "order by" dates | Operations | 2026-11-20 | Ops | High | Not started
Confirm fulfillment staff or 3PL capacity for peak days | Operations | 2026-11-20 | Ops | High | Not started
Write support saved replies (discounts, shipping, returns, order changes) | Support | 2026-11-20 | Support | High | Not started
Plan support coverage and escalation contacts for BFCM weekend | Support | 2026-11-20 | Support | Medium | Not started
Write contingency plan (discount fails, app breaks, payment down, sell-out) | Operations | 2026-11-20 | Ops | Medium | Not started
Send VIP early access | Marketing | 2026-11-24 | Marketing | Medium | Not started
Black Friday launch: publish landing page, banners, emails and ads | Launch | 2026-11-27 | Marketing | High | Not started
Monitor sales, conversion, AOV and margin every few hours | Launch | 2026-11-27 | Marketing | High | Not started
Watch stock and pause promotions on items running low | Launch | 2026-11-27 | Ops | High | Not started
Cyber Monday offer live | Launch | 2026-11-30 | Marketing | High | Not started
Measure results against goals (revenue, AOV, margin, new customers) | After BFCM | 2026-12-04 | Marketing | High | Not started
Send welcome series to first-time buyers | After BFCM | 2026-12-04 | Marketing | Medium | Not started
Request reviews once orders are delivered | After BFCM | 2026-12-10 | Marketing | Medium | Not started
Run Green Monday (Dec 14) and last-shipping-date campaigns | After BFCM | 2026-12-14 | Marketing | Medium | Not started
Write down what worked for BFCM 2027 | After BFCM | 2026-12-18 | Marketing | Low | Not started

## Profit Calculator
BFCM Offer Profit Calculator
Edit the yellow inputs. Shipping, returns and ad spend are excluded. Default values match the illustrative example in the article.
Product selling price ($) | 50
Product cost ($) | 20
Fees + pick/pack per order ($) | 5
Sitewide discount (%) | 25%
Bundle: items per bundle | 2
Bundle discount (%) | 15%
Add-on price ($) | 6
Add-on cost ($) | 1.5
Discount used with add-on offer (%) | 10%
Profit target ($) | 1000
Offer | Shopper pays | Your costs | Profit per order | Orders needed for target
No discount (baseline) | 50 | 25 | 25 | 40
Sitewide discount | 37.5 | 25 | 12.5 | 80
Bundle | 85 | 45 | 40 | 25
Discount + paid add-on | 51 | 26.5 | 24.5 | 41
Revenue = what shoppers pay. Gross profit = revenue minus product cost. Contribution profit (shown here) also subtracts per-order fees and fulfillment. Campaign profit further subtracts ad spend, shipping subsidies and returns.